## Sheet1
Project Management Process Groups
Knowledge Areas | Initiate (2) | Planning (24) | Execute (8) | Communicate and Monitor (11) | Closing (2)
Integration (6) | Develop Project Charter INPUTS • Project Statement of Work (SOW) • Business Case • Agreements TOOLS AND TECHNIQUES • Expert Judgment OUTPUTS • Project Charter PROJECT CHARTER | Develop Project Management Plan INPUTS • Project Charter • Outputs from Other Processes (subsidiary plans) TOOLS AND TECHNIQUES • Expert Judgment • Facilitation Techniques OUTPUTS • Project Management Plan—The MOST IMPORTANT project document PMP | Direct and Manage Project Work INPUTS • Project Management Plan • Approved Change Requests TOOLS AND TECHNIQUES • Facilitation Techniques • Project Management Information Systems • Meetings OUTPUTS • Deliverables • Work Performance Data • Change Requests DELIVERABLE | Control & Monitor Project Work INPUTS • Project Management Plan • Work Performance Information TOOLS AND TECHNIQUES • Project Management Information Systems (Microsoft Project—the tool) • Meetings OUTPUTS • Change Requests (Dr. CPR) • Work Performance Reports—presentation format to be communicated to stakeholders • Project Management Updates • Perform Integrated Change Control WCOP Perform Integrated Change Control INPUTS • Project Management Plan • Work Performance Reports • Change Requests TOOLS AND TECHNIQUES • Meetings • Change Control Tools OUTPUTS • Approved Change Requests (Dr. CPR) • Change Logs • Project Management Updates CHANGE REQUESTS | Close Project or Phase END PRODUCT
Scope (6) |  | Plan Scope Management INPUTS • Project Management Plan • Project Charter TOOLS AND TECHNIQUES • Meetings • Expert Judgment OUTPUTS • Scope Management Plan • Requirements Management Plan Collect Requirements INPUTS • Requirements Management Plan • Stakeholder Management Plan • Stakeholder Register TOOLS AND TECHNIQUES • Focus Groups • Facilitated Workshops • Group Creativity Techniques • Group Decision Making Techniques • Prototype OUTPUTS • Requirements Documentation • Requirements Traceability Matrix Define Scope INPUTS • Scope Management Plan • Requirements Documentation TOOLS AND TECHNIQUES • Product Analysis • Alternatives Generation OUTPUTS • Product Scope Statement Create WBS INPUTS • Project Scope Statement • Requirements Documentation TOOLS AND TECHNIQUES • Decomposition OUTPUTS • Scope Baseline (Project Scope Statement, Work Breakdown Structure, WBS Dictionary) SCOPE BASELINE |  | Validate Scope INPUTS • Requirements Documentation • Requirements Traceability Matrix • Verified Deliverables • Work Performance Data (WPD) TOOLS AND TECHNIQUES • Inspection (always involves customer) • Group Decision Making Techniques OUTPUTS • Accepted Deliverables (Gone through validation of scope) • Change Requests • Work Performance Information (WPI—is WPD analyzed against baseline) Control Scope INPUTS • Requirements Documentation • Requirements Traceability Matrix • Work Performance Data (WPD) TOOLS AND TECHNIQUES • Variance Analysis OUTPUTS • Work Performance Information (WPI—is WPD analyzed against baseline) • Change Requests • PMP Updates • OPA Updates
Time (7) |  | Plan Schedule Management INPUTS • Project Management Plan • Project Charter TOOLS AND TECHNIQUES • Analytical Techniques OUTPUTS • Schedule management plan SCHEDULE MANAGEMENT PLAN Define Activities INPUTS • Schedule Management Plan • Scope Baseline TOOLS AND TECHNIQUES • Decomposition • Rolling Wave Planning (a variation of progressive elaboration) OUTPUTS • Activity List • Activity Attributes • Milestone List ACTIVITY LIST Sequence Activities INPUTS • Activity List • Activity Attributes • Milestones TOOLS AND TECHNIQUES • Precedence Diagram Method (PDM) • Dependency Determination • Leads/Lags OUTPUTS • Project Schedule Network Diagram PROJECT SCHEDULE NETWORK DIAGRAM Estimate Activity Resources INPUTS • Activity List • Activity Attributes TOOLS AND TECHNIQUES • Alternative Analysis • Published Estimating Data • Bottom Up Estimating Data OUTPUTS • Activity Resource Requirements • Resource Breakdown Structure (RBS) ACTIVITY RESOURCE REQUIREMENTS Estimate Activity Durations INPUTS • Activity List • Activity Attributes • Resource Calendars TOOLS AND TECHNIQUES • Analogous Estimating • Parametric Estimating • Three Point Estimating • Group Decision Making Techniques OUTPUTS • Activity Duration Estimates ACTIVITY DURATION ESTIMATES Develop Schedule INPUTS • Activity List • Activity Attributes • Project Schedule Network Diagram • Activity Resource Requirement • Project Staff Requirements • Project Staff Assignments • Resource Breakdown Structure TOOLS AND TECHNIQUES • Critical Path Method • Critical Chain Method • Resource Optimization Techniques • Leads/Lags • Schedule Compression OUTPUTS • Schedule Baseline SCHEDULE BASELINE |  | Control Schedule INPUTS • Work Performance Data (WPD) • Project Schedule TOOLS AND TECHNIQUES • Schedule Compression • Leads/Lags • Modeling Techniques OUTPUTS • Schedule Forecasts • Work Performance Information • Change Requests • OPA Updates • PMP Updates • Project Document Updates
Cost (4) |  | Plan Cost Management INPUTS • Project Charter TOOLS AND TECHNIQUES • Analytical Techniques OUTPUTS • Cost Management Plan Estimate Costs INPUTS • Scope Baseline TOOLS AND TECHNIQUES • Analogous Estimating • Parametric Estimating (Math) • Bottom Up Estimating (Most expensive) • Three Point Estimating (4MOP) • Reserve Analysis (Contingency) • Cost of Quality • Vendor Bid Analysis • Group Decision Making Techniques (DUMP) OUTPUTS • Activity Cost Estimates Determine Budget INPUTS • Scope Baseline • Activity Cost Estimated • Basis of Estimates (BOE) TOOLS AND TECHNIQUES • Cost Aggregation • Funding Limit Reconciliation OUTPUTS • Cost Baseline COST BASELINE |  | Control Costs INPUTS • Project Funding Requirement TOOLS AND TECHNIQUES • Earned Value Management (CV, SV, CPI, SPI) • Forecasting (ETC, EAC) • To Complete Performance Index OUTPUTS • WPI • Change Requests • OPA Updates • PMP Updates • Cost Forecasts WCOP
Quality (3) |  | Plan Quality Management INPUTS • Stakeholder Register • Risk Register TOOLS AND TECHNIQUES • 7 Basic Quality Tools o Cause and Effect Diagrams o Control Chards o Flowcharts o Histograms o Pareto Charts o Run Charts o Scatter Diagrams • Statistical Sampling OUTPUTS • Quality Management Plan • Quality Checklist QUALITY MANAGEMENT PLAN | Perform Quality Assurance INPUTS • Quality Management Plan • Quality Control Measurements TOOLS AND TECHNIQUES • Quality Audit OUTPUTS • Change Requests | Control Quality INPUTS • Project Management Plan • Deliverables TOOLS AND TECHNIQUES • 7 Basic Quality Tools o Cause and Effect Diagrams o Control Chards o Flowcharts o Histograms o Pareto Charts o Run Charts o Scatter Diagrams • Statistical Sampling • Inspection OUTPUTS • Quality Control Measurements • WPU • Change Requests • OPA Updates • PMP updates • Validated Changes • Verified Deliverables VERIFIED DELIVERABLE
Human Resources (4) |  | Plan Human Resource Management INPUTS • Activity Resource Requirements TOOLS AND TECHNIQUES • Organizational Charts and Position Descriptions OUTPUTS • Human Resource Management Plan HUMAN RESOURCE MANAGEMENT PLAN | Acquire Project Team INPUTS • HR Resource Management Plan TOOLS AND TECHNIQUES • Pre-assignment o When • Negotiation • Acquisition OUTPUTS • Project Staff Assignments STAFF ASSIGNMENTS Develop Project Team INPUTS • Project Staff Assignment TOOLS AND TECHNIQUES • Interpersonal Skills • Training • Team Building Activities • Ground Rules • Co-Location • Recognition and Rewards • Personnel Assessment Tools OUTPUTS • Team Performance Assessments TEAM ASSESSMENT Manage Project Team INPUTS • Project Staff Assignment • Team Performance Assessment • Issue Log TOOLS AND TECHNIQUES • Observation and conversation • Project Performance Appraisals • Conflict Management OUTPUTS • Change Requests CHANGE REQUESTS
Communications (3) |  | Plan Communications Management INPUTS • Stakeholder Register TOOLS AND TECHNIQUES • Communication Technology • Communications Model • Communications Methods OUTPUTS • Communications Management Plan COMMUNICATIONS MANAGEMENT PLAN | Manage Communications INPUTS • Work Performance Reports TOOLS AND TECHNIQUES • Communication Models • Communication Methods • Information Management Systems OUTPUTS • Project Communications | Control Communications INPUTS • Project Communications • Issue Log TOOLS AND TECHNIQUES • Information Systems Management OUTPUTS • WPI • Change Requests • OPA Updates • PMP Updates WCOP
Risk (6) |  | Plan Risk Management INPUTS • PMP • Project Management Charter • Stakeholder Register TOOLS AND TECHNIQUES • Analytical Techniques OUTPUTS • Risk Management Plan RISK MANAGEMENT PLAN Identify Risks INPUTS • Risk Management Plan • Scope Baseline TOOLS AND TECHNIQUES • Documentation Review • Information Gathering • Checklist Analysis • Assumptions Analysis • Diagramming Technique • SWOT Analysis OUTPUTS • Risk Register RISK REGISTER Perform Qualitative Risk Analysis INPUTS • Scope Baseline • Risk Register TOOLS AND TECHNIQUES • Risk Probability and Impact Assessment OUTPUTS • Project Document Updates PROJECT DOCUMENT UPDATES Perform Quantitative Risk Analysis INPUTS • Risk Management Plan • Cost Management Plan • Risk Register TOOLS AND TECHNIQUES • Data Gathering and Representation Techniques • Quantitative Risk Analysis and Modeling Techniques OUTPUTS • Project Document Updates PROJECT DOCUMENT UPDATES Plan Risk Response INPUTS • Risk Management Plan • Risk Register TOOLS AND TECHNIQUES • Strategies for Negative Risks • Strategies for Positive Risks • Contingency Response OUTPUTS • PMP Update PMP UPDATE |  | Control Risks INPUTS • Risk Register • Work Performance Reports TOOLS AND TECHNIQUES • Risk Reassessment • Risk Audits • Reserve Analysis OUTPUTS • Work Performance Information • Change Requests • OPA Updates • PMP Updates WCOP
Procurement (4) |  | Plan Procurement Management INPUTS • Requirements Documentation • Risk Register • Activity Resource Requirements • Project Schedule TOOLS AND TECHNIQUES • Make or Buy Analysis OUTPUTS • Procurement SOW • Procurement Documents • Source Selection Criteria • Make or Buy Decision PROCUREMENT MANAGEMENT PLAN | Conduct Procurements INPUTS • Source Selection Criteria • Seller Proposals • Procurement Statement of Work TOOLS AND TECHNIQUES • Bidder Conferences • Independent Estimates • Procurement Negotiations OUTPUTS • Selected Sellers, Agreements SELECTED SELLERS, AGREEMENTS | Control Procurements INPUTS • Procurement Documents • Agreements • Approved Change Requests TOOLS AND TECHNIQUES • Procurement Performance Information • Inspections and Audits • Performance Reporting • Payment Systems • Claims administrations • Records Management Systems OUTPUTS • Work Performance Information (WPI) • Change Requests • OPA Updates • PMP Updates WCOP | Close Procurements INPUTS • Procurement Documents (alphabet soup, RFP, RFQ etc) TOOLS AND TECHNIQUES • Procurement Audits • Negotiated Settlement OUTPUTS • Closed Procurements • OPA Updates
Stakeholders (4) | Identify Stakeholders INPUTS • Project Charter • Procurement Documents/Agreements (Engage outside of project team) TOOLS AND TECHNIQUES • Stakeholder Analysis OUTPUTS • Stakeholder Register STAKEHOLDER REGISTER | Plan Stakeholder Management INPUTS • Project Management Plan • Stakeholder Register TOOLS AND TECHNIQUES • Analytical Techniques OUTPUTS • Stakeholder Management Plan STAKEHOLDER MANAGEMENT PLAN | Manage Stakeholder Engagement INPUTS • Stakeholder Management Plan TOOLS AND TECHNIQUES (MCI) • Management Skills • Communication Methods • Interpersonal Skills OUTPUTS • Issue Log • Change Requests • OPA (Organizational Process Assets) Updates • PMP Updates • Project Document Updates ISSUE LOG | Control Stakeholder Engagement INPUTS • Project Management Plan • Issue Log • Work Performance Data (WPD) TOOLS AND TECHNIQUES • Information System OUTPUTS • Work Performance Information (WPI—attained by comparing WPD to PMP) • Change Request • OPA Updates (Organizational Process Assets) • Project Management Plan Updates WCOP
KEYWORDS | INITIATE | PLAN | EXECUTE | MONITOR AND CONTROL | CLOSE
| Initial | Collect | Implement | Forecast | Finish
| Start | How To | Build | Track | Complete
| High Level | Strategy | Issues | Report | Terminate
|  | Approach | Do | Verify | Finalize
|  | Document | Conduct | Review | End
|  | Determine |  | Validate | Settlement
|  | Detail |  | Compare
|  | Estimate |  | Measure
Requirements
Create
Sequence
Dependency